## Sheet1
Ref. | Phase | Commitment | Topics | Responsibility | Source Document | Management Plan Reference | Project Worksite
0 | 1 | 2 | 3 | 4 | 5 | 6 | 8
1 | Construction | EPC will implement mitigation measures to control nuisance dust and particulate emmissions, as follows: ■ Enforce a speed limit of 30 km/h on unpaved surfaces, especially the access road to the site, and the national speed limits on public roads should not be exceeded; ■ Maintain all construction vehicles regularly to minimise exhaust emissions; ■ When not in use, vehicles will be switched off, unless impractical for health and safety reasons (for example, maintenance of air conditioning); ■ Exercise traffic planning and control: avoid driving through settlements and close to residential areas, travel planning to minimise congestions, etc. ■ Perform proper fleet management: use modern vehicles meeting up to date emission limits, routine maintenance, use of low sulphur fuels. | Air Emissions Construction Traffic | EPC | ESIA 2023 | Pollution Prevention & Control Plan | Site Construction Laydown Area Temporary Access Roads
2 | Construction | Mitigations to addres construction dust ■ Restrict the area for the removal of vegetation and soil cover to that only necessary for the Project; ■ Land clearance should be sequential and where ground and earthworks are undertaken the smallest possible area for working will be exposed; ■ Stripping of topsoil will not be conducted earlier than required (maintain vegetation cover for as long as possible) in order to prevent the erosion (wind and water) of organic matter, clay and silt. ■ Access road is to be wetted, especially during the dry season, and when construction activities are in progress, and especially in those areas in close proximity to residential homesteads (< 200 m). ■ All transported bulk materials must be covered with tarpaulins to prevent fugitive dust emissions; ■ Stockpiles stored longer than six weeks should be vegetated to reduce soil loss from wind or storm water runoff; ■ Stockpiles will be located as far away from receptors as possible. | Air Emissions Construction Dust | EPC | ESIA 2023 | Pollution Prevention & Control Plan | Site Construction Laydown Area Temporary Access Roads
3 | Construction | Mitigations to address Soil compaction and erosion ■ Sites/vegetation clearance, sites preparation, excavations, and improvement of existing roads and construction of additional access roads should not be carried out during periods of torrential rains or storms and heavy wind, to minimize compaction and erosion; ■ Rehabilitation interventions in the priority areas (i.e. areas where there is a low likelihood of natural revegetation or where areas are prone to compaction and erosion from surface runoff) should be prioritised; ■ Should compaction and erosion events be identified, appropriate remedial actions, including restoration of the compacted and/or eroded areas, and where necessary, the relocation of the paths causing the compaction and/or erosion, should be undertaken, ■ Land/vegetation clearance should only be undertaken immediately prior to construction activities taken place there, ■ Unnecessary land/vegetation clearance should be avoided, ■ The footprints for all construction sites and areas for associated facilities/infrastructure (e.g. borrow and disposal areas, lay-down areas, construction/management sites and temporary offices) should be restricted to minimum feasible extent with measures implemented to avoid footprint creep, ■ Unless foreign material, such as aggregate (e.g. crushed stone, ballast, gravel, sand), needs to be inserted, after the installation of features requiring the excavation of a deep holes, soil should be replaced in the holes so as to mimic the pre-construction profile. | Geology and Soil | EPC | ESIA 2023 | Topsoil Management and Site Reinstatement Plan | Site Construction Laydown Area Temporary Access Roads
4 | Construction | Mitigations to addresss Soil contamination ■ Contract a licensed contractor to collect, transport and treat domestic, construction and hazardous wastes from Project sites, ■ Prohibit dumping any types of solid waste to the soil, or burning waste of sites, ■ Ensure that hazardous materials are stored in designated areas that are designed with impermeable floor, inflammable walls and accessible to authorized personnel, ■ Hazardous waste shall be properly managed in accordance with existing legislation on hazardous waste ■ Maintenance works are restricted to specially designated platforms with strict control of accidental spills, ■ Procedures for responding to emergencies / accidental spills of hazardous materials, fuel and handling, and waste management are developed and implemented, ■ In case of accidental/unintended spillage, the contaminated soil should be immediately collected and stored as hazardous waste. | Geology and Soil | EPC | ESIA 2023 | Pollution Prevention & Control Plan; Waste Management Plan | Site Construction Laydown Area Temporary Access Roads
5 | Construction | Mitigation measures to address Impact on Water Quality (groundwater and surface water resources) ■ Install sediment traps and culverts as part of the drainage infrastructure around the Project sites prior to clearance and earthorks, so as to prevent any sediment run-off into the surrounding area. ■ Provide culverts along new access roads to facilitate drainage along with ditches. Where practical, exposed surfaces and friable materials should be covered. ■ Provide sufficient toilets at active work areas for staff and workers and these should be serviced regularly by a competent and suitably qualified person. ■ Contractors and applicable Project staff should be trained regarding proper methods for transporting, transferring and hazardous substances that have the potential to impact water resources. ■ Areas where spillage of contaminants occurs should be excavated (to the depth of contamination) and suitably rehabilitated. If any other minor spillage occurs, it should be cleaned immediately, and the contaminated area should be rehabilitated. ■ The washing of Project vehicles in any surface water bodies in and around Project site(s) will be strictly prohibited. All Project vehicles should be washed at designated washbays on site/s. These wash bays will include oil/grease and sediment traps for grey water. ■ Prevent any ad-hoc maintenance of vehicles/equipment in and around the Project site(s). All vehicles/equipment should be maintained at a designated workshop. The workshop will include an oil/grease trap. ■ Maintain sll active work areas in a good and tidy condition; debris and waste should be contained in such a way that they cannot become entrained into surface run during periods of heavy rain. ■ The management of sewage should be taken over by a licenced contractor . ■ Provide hazardous waste storage areas with secondary containment. Moreover, hazardous waste should be stored in sealed/covered containers to prevent rainwater intrusion. ■ Provide all dangerous and hazardous material stores and handling areas with secondary containment capable of holding 110% of the total capacity of all tanks/vessels. ■ Confine the loading and unloading of dangerous and hazardous material to areas that are provided with secondary containment and in line with hazardous material handling procedures. | Groundwater and Surface Water | EPC | ESIA 2023 | Pollution Prevention & Control Plan | All Project Worksites
6 | Construction | Mitigation measures to address Impact on Water Quantity/Water Abstraction ■ Before groundwater is selected as a source of water for the Project, a thorough assessment should be conducted on water availability and vulnerability in and around Project site(s). These studies should be undertaken by a suitably qualified specialist and should ensure that the design of the Project water supply scheme is such that it minimises and avoids abstraction rates beyond the safe yield volume and subsequent impacts to sensitive social receptors. ■ Abstraction from surface water should be avoided. ■ Operation and management of water abstraction should be undertaken in such a way that the rate of abstraction is monitored against safe yield abstraction rates. | Groundwater and Surface Water | EPC | ESIA 2023 | Pollution Prevention & Control Plan | All Project Worksites
7 | Construction | ■ Develop and implement a Grievance procedure in the event of any water reduction and subsequent water availability complaints being received. | Groundwater and Surface Water | Project Owner | ESIA 2023 | Stakeholder Engagement Plan | All Project Worksites
8 | Construction | ■ Segregate and identify domestic solid waste from the other waste streams into separate waste containers/skips clearly to facilitate recycling and reuse. ■ Clearly label waste containers/skips and place them in designated waste storage locations. Labels will be waterproof, securely attached, and written in Romanian. ■ Place an adequate number of covered bins for litter (food waste, domestic waste) throughout the sites at locations where staff consume food. These will be regularly collected and taken to the waste storage area/landfill. ■ Store food waste within a sealed metal or plastic skip or bin, in order to prevent pests gaining access. ■ Contain heavy waste within an open skip, provided that segregation occurs effectively enough to remove all lightweight material that could be blown away. ■ Recycle and reuse waste generated during construction until reduced to as low as practicable, prior to collection for disposal by an appropriately licenced waste contractor. ■ Engage only waste transporters and waste management facilities. ■ Develop and maintain a waste inventory to document and track domestic solid waste generated, segregated, reused and consignments. ■ Completed waste record reports are required to show the chain of custody of the waste generated on site, its transportation and treatment/disposal. All records will be maintained on site. ■ Mandatory training program for employees to increase their awareness of waste management protocols including proper handling and storage of waste, recycling waste, reusing plastics, wood & other reusable non-hazardous materials. ■ Identify recycling companies in Buzau County or in the the region in order to implement the recycling of waste. ■ Develop and maintain a hazardous waste inventory to document and track hazardous wastes generated, segregated, reused and consignments. ■ Segregate and identify hazardous waste from the other waste streams into separate signed and labeled waste containers/skips. ■ Store hazardous waste in allocated hard standing areas in sealed containers stored with impermeable bases, sufficient containment and separation capacity, sun/rain shelter, separate drainage system, good ventilation and equipped with spill kits & spill response procedures. This area must be placed away from any sources of ignition. ■ Hazardous waste storage area will be constructed away from drainage system and a rain shelter will be provided to avoid any potential instance of runoff, or leakage of runoff. ■ Waste containers will be clearly marked with appropriate warning labels to accurately describe their contents and safety precautions. Labels will be waterproof, securely attached, and written in Romanian. Wherever possible, chemicals will be kept in their original container. ■ Hazardous waste storage areas will be located away from any ignition sources or fire hazards. ■ Develop and maintain a hazardous waste inventory to document and track sanitary waste generated and segregated. ■ Sanitary wastewater tanks to be properly maintained and inspected to ensure tanks do not overflow. ■ Site inspections will be carried out regularly by the EPC Contractor to ensure that all wastewater generated is properly managed, and no leakages or spill occur. In the event of a spill or overflow, immediate action will be taken in accordance with spill containment procedures and clean up procedures. ■ Engage a licensed waste/wastewater contractor for the periodic removal of septic tanks. | Waste and Wastewater | EPC | ESIA 2023 | Waste Management Plan | All Project Worksites
9 | Construction | ■ In-situ testing of soil to ensure it is not contaminated and can be reused or disposed into land. ■ Training –Contractor staff to be able to identify signs of potential contamination (smell of HC, staining). | Waste and Wastewater | EPC | ESIA 2023 | Waste Management Plan | All Project Worksites
10 | Construction | ■ Undertake concrete washout in designated and signed areas to prevent leaks or spread of wastewater. ■ Construct the concrete washout area and maintaine it in sufficient quantity and size to contain all liquid and concrete waste generated by washout operations. ■ The concrete washout area will have an impermeable surface with dedicated drainage systems. ■ Undertake the removal of any sludge residues as solid hazardous waste only by a licensed waste/wastewater contractor and handle as a hazardous waste. | Waste and Wastewater | EPC | ESIA 2023 | Waste Management Plan | All Project Worksites
11 | Construction | ■ Store any generated medical waste in appropriate medical waste containers. ■ Handle all medical waste only by trained personnel. ■ Conduct the removal of any medical waste from the site for appropriate treatment, disposal/incineration will only by a licensed contractor. | Waste and Wastewater | EPC | ESIA 2023 | Waste Management Plan | All Project Worksites
12 | Construction | ■ Demarcate the construction zone or servitude for the TL corridor on a map and on the ground clearly using high visibility tape for instance, to avoid impacting on sensitive areas outside of the permitted construction area; | Designated and Protected Areas | EPC | ESIA 2023 | Biodiversity Management Plan | All Project Worksites
13 | Construction | ■ Reinstate temporary land take to original use after completion of construction | Designated and Protected Areas | EPC/Owner | ESIA 2023 | Topsoil Management and Site Reinstatement Plan | All Project Worksites
14 | Construction | ■ Avoid locating construction camps and material/equipment laydown areas within or near identified natural or semi-natural habitat; | Designated and Protected Areas | EPC | ESIA 2023 | Biodiversity Management Plan | All Project Worksites
15 | Construction | ■ Utilise existing roads wherever possible. | Designated and Protected Areas | EPC | ESIA 2023 | Traffic Management Plan | Site Construction Laydown Area Temporary Access Roads
16 | Construction | ■ Implement relevant construction standards (e.g. ‘Construction Code of Practice for the Sustainable Use of Soils on Construction Sites’ – DEFRA, 20096F6F ). Demarcate the construction zone or servitude for the TL corridor on a map and on the ground clearly using high visibility tape for instance, to avoid impacting on sensitive areas outside of the permitted construction area; | Habitats Habitat Loss / Degradation / Fragmentation | EPC | ESIA 2023 | Topsoil Management and Site Reinstatement Plan | All Project Worksites
17 | Construction | ■ Avoid locating construction camps and material/equipment laydown areas within or near identified natural or semi-natural habitat; | Habitats Habitat Loss / Degradation / Fragmentation | EPC | ESIA 2023 | Biodiversity Management Plan | All Project Worksites
18 | Construction | ■ Compile a suitable post-construction habitat restoration plan for temporary areas used during construction; | Habitats Habitat Loss / Degradation / Fragmentation | Owner | ESIA 2023 | Biodiversity Management Plan | All Project Worksites
19 | Construction | ■ Use existing access roads or upgrade existing roads wherever possible before considered new access road construction; | Habitats Habitat Loss / Degradation / Fragmentation | EPC/Owner | ESIA 2023 | Traffic Management Plan | Site Construction Laydown Area Temporary Access Roads
20 | Construction | ■ Place appropriate limits on the number of vehicle movements to and from the wind farm; | Habitats Habitat Loss / Degradation / Fragmentation | Owner | ESIA 2023 | Traffic Management Plan | Site Construction Laydown Area Temporary Access Roads
21 | Construction | ■ Restrict vehicles to the use of only authorized access roads; | Habitats Habitat Loss / Degradation / Fragmentation | EPC/Owner | ESIA 2023 | Traffic Management Plan | Site Construction Laydown Area Temporary Access Roads
22 | Construction | ■ Compile a suitable Invasive Alien Plant (IAP) species control plan and programme to manage IAP’s within the control of the development; | Habitats Introduction/Spread of Invasive Species | Owner | ESIA 2023 | Invasive Species Management Plan | All Project Worksites
23 | Construction | ■ Implement IAP species surveillance and control plan within areas in the projects control, focusing particularly on areas of natural habitat; | Habitats Introduction/Spread of Invasive Species | Owner | ESIA 2023 | Invasive Species Management Plan | All Project Worksites
24 | Construction | ■ Monitor IAPs to inform further management intervention. | Habitats Introduction/Spread of Invasive Species | Owner | ESIA 2023 | Invasive Species Management Plan | All Project Worksites
25 | Construction | ■ Implement buffer zones or exclusion areas around important nesting or foraging sites to minimize disturbance; | Birds Habitat Loss / Degradation / Fragmentation | Owner | ESIA 2023 | Biodiversity Management Plan | All Project Worksites
26 | Construction | ■ Avoid site clearance during the breeding season. Where not, use Ecological Clerks of Works to identify nests and avoid till young have fledged. | Birds Habitat Loss / Degradation / Fragmentation | Owner | ESIA 2023 | Biodiversity Management Plan | All Project Worksites
27 | Construction | ■ Implement construction practices that minimize noise and vibration disturbance, such as scheduling activities outside sensitive bird breeding periods or using noise barriers; | Birds Noise and Vibration Disturbance | EPC/Owner | ESIA 2023 | Biodiversity Management Plan | All Project Worksites
28 | Construction | ■ Avoid site clearance during the breeding season. Where not, use Ecological Clerks of Works to identify nests and avoid till young have fledged; | Birds Noise and Vibration Disturbance | EPC/Owner | ESIA 2023 | Biodiversity Management Plan | All Project Worksites
29 | Construction | ■ Avoid site clearance during the breeding season. Where not, use “Ecological Clerk of Works” (ECoW) which will prepare the environmental documentation on delivery of ecological requirements on site before construction activities commence in order for contractors to meet key development milestones; The ECoW will monitor that site based construction activities are delivered in accordance to relevant laws and Project commitments; | Birds Direct Mortality | EPC/Owner | ESIA 2023 | Biodiversity Management Plan | All Project Worksites
30 | Construction | ■ Install fence and mark work areas to minimise effects of vegetation clearance on birds. | Birds Direct Mortality | EPC/Owner | ESIA 2023 | Biodiversity Management Plan | All Project Worksites
31 | Construction | ■ Install overhead transmission line and pylons ■ Conduct thorough surveys to identify and protect nesting sites before construction begins. Implement buffer zones around active nests and restrict construction activities within these areas during breeding season; | Birds Installation of overhead transmission line and pylons | Owner | ESIA 2023 | Biodiversity Management Plan | All Project Worksites
32 | Construction | ■ Install overhead transmission line and pylons ■ Fit suitable bird diverters at 5m intervals | Birds Installation of overhead transmission line and pylons | Owner | ESIA 2023 | Biodiversity Management Plan | All Project Worksites
33 | Construction | ■ Install overhead transmission line and pylons ■ Install insulation, covers, and other avian protection devices on electrical equipment to prevent perching and contact. Regularly inspect and maintain the electrical infrastructure to ensure its effectiveness in mitigating electrocution risks. | Birds Installation of overhead transmission line and pylons | Owner | ESIA 2023 | Biodiversity Management Plan | All Project Worksites
34 | Pre-construction | ■ Conduct pre-construction checks for presence of bat roosts near construction sites; | Bats Habitat Loss / Degradation / Fragmentation | Owner | ESIA 2023 | Biodiversity Management Plan | All Project Worksites
35 | Construction | ■ Implement noise reduction measures to minimize noise-related disturbance near bat roosts; | Bats Habitat Loss / Degradation / Fragmentation | Owner | ESIA 2023 | Biodiversity Management Plan | All Project Worksites
36 | Construction | ■ Control of lighting to prevent light spill outside of construction areas through use of directional cowls. | Bats Habitat Loss / Degradation / Fragmentation | Owner | ESIA 2023 | Biodiversity Management Plan | All Project Worksites
37 | Construction | ■ Establishing buffer zones around bat roosts; | Bats Direct mortality | Owner | ESIA 2023 | Biodiversity Management Plan | All Project Worksites
38 | Construction | ■ Adjust construction schedules to avoid sensitive periods; | Bats Direct mortality | EPC/Owner | ESIA 2023 | Biodiversity Management Plan | All Project Worksites
39 | Construction | ■ Implement proper lighting protocols to minimize disturbance. | Bats Direct mortality | Owner | ESIA 2023 | Biodiversity Management Plan | All Project Worksites
40 | Pre-construction | ■ Conduct pre-construction surveys where Spermophilus citellus habitats were identified within 100m of turbines during the baseline studies; | Mammals Spermophilus citellus Habitat Loss / Degradation / Fragmentation. Direct loss of species | Owner | ESIA 2023 | Biodiversity Management Plan | All Project Worksites
41 | Construction | ■ Establish temporary exclusion zones around sensitive Spermophilus citellus habitats to prevent destruction of burrows. Create buffer areas around key habitat zones to reduce noise levels, limit human activity; | Mammals Spermophilus citellus Habitat Loss / Degradation / Fragmentation. Direct loss of species | Owner | ESIA 2023 | Biodiversity Management Plan | All Project Worksites
42 | Construction | ■ Implement strict construction protocols to minimize disturbance to the species, including complying to specified working hours to minimize noise, implementing dust control measures to maintain air quality and utilize appropriate barriers to prevent unintentional access to construction areas; | Mammals Spermophilus citellus Habitat Loss / Degradation / Fragmentation. Direct loss of species | Owner | ESIA 2023 | Biodiversity Management Plan | All Project Worksites
43 | Construction | ■ Implement a robust monitoring program during the construction phase to assess the impact on Spermophilus citellus and their habitat. This includes regular surveys, population monitoring and tracking of individuals. If unexpected impacts are observed, use adaptive management strategies to modify construction practices and mitigate any negative effects on the population; | Mammals Spermophilus citellus Habitat Loss / Degradation / Fragmentation. Direct loss of species | Owner | ESIA 2023 | Biodiversity Management Plan | All Project Worksites
44 | Construction | ■ Establish exclusion zones or limiting construction activities in close proximity to active burrows; | Mammals Spermophilus citellus Noise and vibrance | Owner | ESIA 2023 | Pollution Prevention and Control Plan | All Project Worksites
45 | Construction | ■ Use noise barriers and muffers on construction equipment; | Mammals Spermophilus citellus Noise and vibrance | Owner | ESIA 2023 | Pollution Prevention and Control Plan | All Project Worksites
46 | Construction | ■ Undertake pre-construction surveys for otters 200m up and downstream of waterway crossings to identify any breeding or resting areas; | Mammals Lutra lutra Habitat Loss / Degradation / Fragmentation | Owner | ESIA 2023 | Biodiversity Management Plan | All Project Worksites
47 | Construction | ■ Implement measures to avoid disturbance of holts or resting places such as set back distances or timing of works; | Mammals Lutra lutra Habitat Loss / Degradation / Fragmentation | Owner | ESIA 2023 | Biodiversity Management Plan | All Project Worksites
48 | Construction | ■ Designate and protect riparian buffer zones along Călmățui riverbanks while consolidating the crossing over it. These zones will act as a protective buffer, maintaining the integrity of the otter`s habitat and minimizing the risk of disturbance; | Mammals Lutra lutra Habitat Loss / Degradation / Fragmentation | Owner | ESIA 2023 | Biodiversity Management Plan | All Project Worksites
49 | Construction | ■ Implement best practice for river crossings to prevent deterioration of water quality (e.g. Scottish Environmental Protection Agency (2010). Engineering in the water environment: good practice guide River Crossings); | Mammals Lutra lutra Habitat Loss / Degradation / Fragmentation | Owner | ESIA 2023 | Biodiversity Management Plan | All Project Worksites
50 | Construction | ■ Implement strict noise and disturbance control measures during the construction phase of the wind farm. This includes limiting construction activities during sensitive periods. | Mammals Lutra lutra Habitat Loss / Degradation / Fragmentation | Owner | ESIA 2023 | Biodiversity Management Plan | All Project Worksites
51 | Construction | ■ Monitor water quality parameters regularly to identify any potential impacts and take corrective actions if necessary | Mammals Lutra lutra Water Quality | Owner | ESIA 2023 | Biodiversity Management Plan | All Project Worksites
52 | Construction | ■ Establish exclusion zones or limiting construction activities in close proximity to active otter dens or habitats; | Mammals Lutra lutra Noise and Vibration | Owner | ESIA 2023 | Biodiversity Management Plan | All Project Worksites
53 | Construction | ■ Use noise barriers and muffers on construction equipment; ■ Monitor noise and vibration levels regularly to ensure compliance with regulatory standards; | Mammals Lutra lutra Noise and Vibration | Owner | ESIA 2023 | Biodiversity Management Plan | All Project Worksites
54 | Construction | ■ Schedule noisy activities during periods of low otter activity or avoid sensitive breeding season. | Mammals Lutra lutra Noise and Vibration | Owner | ESIA 2023 | Biodiversity Management Plan | All Project Worksites
55 | Construction | ■ Conduct thorough surveys and assessments to identify the presence of herpetofauna species and their habitats before construction activities; | Herpetofauna Habitat Loss/ Degradation / Fragmentation | Owner | ESIA 2023 | Biodiversity Management Plan | All Project Worksites
56 | Construction | ■ Implement best management for river crossings (SEPA 2010). | Herpetofauna Habitat Loss/ Degradation / Fragmentation | Owner | ESIA 2023 | Biodiversity Management Plan | All Project Worksites
57 | Construction | ■ Establish buffer zones and construction exclusion zones around sensitive herpetofauna habitats to minimize disturbance; | Herpetofauna Noise and Vibration Disturbance | Owner | ESIA 2023 | Biodiversity Management Plan | All Project Worksites
58 | Construction | ■ Implement noise and vibration mitigation measures such as limiting noisy activities during sensitive periods (e.g., breeding season) and use equipment with noise reduction technologies. | Herpetofauna Noise and Vibration Disturbance | Owner | ESIA 2023 | Biodiversity Management Plan | All Project Worksites
59 | Construction | ■ Implement pollution control practice including appropriate storage and containement, refuelling stations away from water bodies, availability and training in use of spill kits; | Herpetofauna Water pollution |  | ESIA 2023 | Pollution Prevention and Control Plan | All Project Worksites
60 | Construction | ■ Conduct regular water quality testing at strategic locations; | Herpetofauna Water pollution |  | ESIA 2023 | Pollution Prevention and Control Plan | All Project Worksites
61 | Construction | ■ Monitor key parameters such as pH, dissolved oxygen levels, turbidity and presence of specific polluants; | Herpetofauna Water pollution |  | ESIA 2023 | Pollution Prevention and Control Plan | All Project Worksites
62 | Construction | ■ Establish clear protocols for reporting and responding to any water pollution incidents, including immediate corrective actions. | Herpetofauna Water pollution |  | ESIA 2023 | Pollution Prevention and Control Plan | All Project Worksites
63 | Construction | ■ Establish avoidance and exclusion zones around known reptile habitats to minimise risk of direct impacts. Clearly mark and communicate these zones to construction personnel to ensure compliance; | Herpetofauna Direct loss of species | Owner | ESIA 2023 | Biodiversity Management Plan | All Project Worksites
64 | Construction | ■ Implement a relocation plan. This involves capturing and translocating reptiles to suitable habitats away from the construction zone, ensuring their safety; | Herpetofauna Direct loss of species | Owner | ESIA 2023 | Biodiversity Management Plan | All Project Worksites
65 | Construction | ■ Provide comprehensive training to construction workers and equipment operators on reptile conservation and the importance of implementing mitigation measures; | Herpetofauna Direct loss of species | Owner | ESIA 2023 | Biodiversity Management Plan | All Project Worksites
66 | Construction | ■ Identify and compensate all land users for reduction in subsidies, including both formal and informal land users and prior to accessing the land; ■ Provide compensation for loss of assets at replacement cost; ■ Ensure appropriate disclosure of information, consultation, and the informed participation of those affected; ■ Improve or, at a minimum, restore the livelihoods and standards of living of affected persons to pre-project levels, so as to facilitate sustainable improvements to socio-economic status; | Livelihood | EPC | ESIA 2023 | Land Acquisition and Livelihoods Restoration PlanPlan | All Project Worksites
67 | Construction | ■ Selection criteria, job profiles, and number of workers for the construction phase with specific attention to the enhancement of the local community, women, and vulnerable groups’ employment. ■ Clear communication of required involvement of local workforce and local companies, explaining requirements on qualification, availability, eventual training, etc. ■ Description of the recruitment process and details of the recruitment information disclosure to local communities. ■ Details of vocational trainings available to employed construction workers. ■ Description of the Worker’s Code of Conduct, highlighting labour conditions with an aim to reduce the risk of gender-based violence and harassment. ■ Details of worker’s grievance mechanism that will be disclosed during the recruitment process and the employment period. ■ A commitment to provide workers with a sufficient notice period as to when their job contract terminates. ■ Monitoring indicators and the reporting timeline for the recruitment process and management of the workforce. | Economy, Employment and Income | Project Owner | ESIA 2023 | Workforce Management Plan | All Project Worksites
68 | Construction and Operation | ■ Ensure regular, open and transparent communication with all stakeholders | Economy, Employment and Income | Project Owner | ESIA 2023 | Stakeholder Engagement Plan | All Project Worksites and location, Social AoI
69 | Construction | ■ Ascertain, prior to the construction phase, whether the local services are sufficient for workforce influx and, where appropriate, liaise with relevant authorities to limit the negative impact of the Project on local users' access to public services. | Infrastructure and Public Services | Project Owner | ESIA 2023 | Workforce Management Plan | All Project Worksites
70 | Construction | ■ The WTGs will be equipped with anti-collision lighting and marking systems in line with the national standards and/or good industry practices to prevent possible accidents with aviation. | Community Health and Safety | Project Owner | ESIA 2023 | N/A - Project Design aspect | All Project Worksites
71 | Construction | ■ Enhancement of local employment through sourcing employees from the direct Social Aoi and limiting the numbers of non-local workers. | Community Health and Safety | Project Owner | ESIA 2023 | Workforce Management Plan | Social AoI
72 | Construction | ■ Enforcement of Workers’ Code of Conduct containing a set of rules on behavioural standards and cultural awareness requirements for all employees (including security personnel) | Community Health and Safety | Project Owner | ESIA 2023 | Workforce Management Plan | All Project Worksites
73 | Construction | ■ Provide workers with safety equipment to prevent occupational health issue and reduce the number of accidents at work; | Labour and working conditions | EPC | ESIA 2023 | Health & Safety Management Plan | All Project Worksites
74 | Construction | ■ Provide regular training on first aid and safety responses in order to limit accidents’ impact on workers’ health; | Labour and working conditions | EPC | ESIA 2023 | Health & Safety Management Plan | All Project Worksites
75 | Construction | ■ Hold safety briefings with the employed labour force to ensure greater attention to detail and safety, especially when performing work activities in dangerous environments, i.e. working at heights during the wind turbine construction; | Labour and working conditions | EPC | ESIA 2023 | Health & Safety Management Plan | All Project Worksites
76 | Construction | ■ Ensure that the appropriate accommodation is provided to all workers, in line with IFC PS2 and national requirements. | Labour and working conditions | EPC | ESIA 2023 | Workforce Management Plan | All Project Worksites
77 | Construction | ■ Demarcate construction boundaries and minimize areas of surface disturbance; ■ Where possible, locate laydown areas and construction camps in areas that are already disturbed or cleared of vegetation; ■ For the construction site maintenance, conduct good housekeeping on site to avoid litter and minimize waste; ■ Use existing tracks/roads for access, where possible; and ■ Within the environmental management system, prepare a restoration management plan including replanting indigenous species, and landscaping and rehabilitating construction yards. | Landscape | EPC | ESIA 2023 | Topsoil Management and Site Reinstatement Plan | All Project Worksites
78 | Construction and Operation | ■ Where possible, locate laydown areas and construction camps in areas that are already disturbed or cleared of vegetation; ■ For the construction site maintenance, conduct good housekeeping on site to avoid litter and minimize waste; ■ Minimize night lighting while guaranteeing the minimum safety level; ■ Use of materials that will minimize light reflection should be used for all Project components; ■ Existing vegetation should be retained to the greatest extent possible. Vegetation should be retained along roads, and other Project infrastructure | Visual | EPC | ESIA 2023 | Topsoil Management and Site Reinstatement Plan; Health & Safety Management Plan | All Project Worksites
79 | Construction and Operation | ■ Rehabilitation of all viable disturbed areas (e.g. temporary access tracks and laydown areas) must be undertaken following construction. This must be done in such a way so as to facilitate natural regeneration of vegetation; ■ Maintain ongoing engagement between the Project and local communities, with communities informed in advance of any vegetation clearing to allow pre-harvesting of resources such as building materials or other useable resources. | Ecosystem Services | EPC | ESIA 2023 | Topsoil Management and Site Reinstatement Plan: Stakeholder Engagement Plan | All Project Worksites
80 | Construction and Operation | ■ Compensate land users for the loss of their specific interest in part of the pastureland for a period of time and assistt them in their re-establishment, if required, once the constructions works are completed | Livelihood Ecosystem services | Project Owner | ESIA 2023 | Livelihood Restoration Plan | All Project Worksites
81 | Construction | ■ Work with local authorities in scheduling truck deliveries, especially oversized truck deliveries, to reduce impacts on road function and safety. Specifically: - Where safe and feasible, schedule deliveries to minimize travel impacts for other road users based upon local conditions and the results of stakeholder engagement. Consider scheduling deliveries during non-peak hours and at intervals to avoid queuing of delivery vehicles along public roads near the access points to internal Project roads. (construction, operations, decommissioning). - Consider scheduling deliveries, especially the oversized turbine components, in convoys of multiple trucks at one time to reduce the frequency of road travel interruption and delays. (construction, decommissioning). - Consider movement of oversized or escorted loads at night, if feasible and safe, to reduce impact to road function. (construction, operations, decommissioning). | Traffic | EPC | ESIA 2023 | Traffic and transport Management Plan | All Project Worksites
82 | Construction | ■ Regularly inform, educate, and update stakeholders and communities close to transport routes about Project traffic, especially about the safety issues and scheduling associated with movement of heavy and oversized loads on public roads. | Traffic | Project Owner | ESIA 2023 | Traffic Management Plan; Stakeholder Engagement Plan | All Project Worksites
83 | Construction, Operation, Decommissioning | ■ Obtain necessary permits and implement all necessary road improvements or alterations prior to use of the routes for oversized Project shipments. (construction, operations, decommissioning). ■ Restore signs, street lights and other street furniture removed for or damaged by the movement of Project-related trucks. (construction, operations, decommissioning). ■ Survey the condition of roads to be used for concrete, supply, equipment, and component deliveries prior to construction and submit reports to local road authorities. (pre-construction). ■ Repair road damage resulting from construction traffic during the 18 months construction period (construction). ■ Upon completion of the construction and decommissioning phases, work with local road authorities to identify damage to and restore county, communal, and agricultural roads used for Project-related heavy truck traffic. Coordinate with national road authorities (the Romanian National Road Infrastructure Company, or CNAIR) to coordinate and contribute to repair and maintenance of national roads damaged by construction. (construction, decommissioning). ■ Upon completion of construction, install road signage for the new public roads built for the Project as required by the local road authorities. (construction). ■ Upon completion of construction, in coordination with local road authorities and stakeholders, establish a schedule to be implemented by the Proponent and other stakeholders for maintenance of roads within the Project area during wind farm operations. (construction). | Traffic | EPC | ESIA 2023 | Traffic and transport Management Plan | All Project Worksites
84 | Construction, Operation, Decommissioning | ■ Address transportation safety risks of Project traffic, including (but not limited to) truck routes, hours of transport, community notification, signage, education, and other measures to minimize safety hazards. (construction, decommissioning) ■ Obtain permits and implement alterations prior to deliveries. If necessary, construct bypasses to avoid hazards to properties or other road users at constrained road segments or intersections. (pre-construction, construction, decommissioning) ■ Plan truck routes for non-oversized loads using roads with adequate geometrics and load-bearing capacity for safe passage. (pre-construction, construction, operations, decommissioning) ■ Consider community schedules that result in higher levels of local traffic, school schedules, or community events. Schedule truck traffic outside of these times in addition to avoiding periods of peak traffic volumes. (construction, operations, decommissioning) | Traffic | EPC | ESIA 2023 | Traffic Management Plan | All Project Worksites
85 | Construction, Operation, Decommissioning | ■ Establish and implement standards addressing the following: - Training and accreditation for project drivers, including contractors. - Driver fitness standards, including mandatory rest periods and prohibition of drug/alcohol use. - In-vehicle monitoring systems to monitor vehicle speed and location (Project vehicles and contractors). - Project and contractor standards for vehicle safety and maintenance. - Security response for vehicle incidents. - Load stability standards. | Traffic | EPC | ESIA 2023 | Traffic Management Plan | All Project Worksites
86 | Construction | ■ Design and implement a Chance Finds Procedure to manage any unexpected discovery of archaeological material in-line with international requirements and guidelines IFC PS8. | Cultural Heritage | EPC | ESIA 2023 | Cultural Heritage Management Plan | All Project Worksites
87 | Operation | ■ Continuously assess identified and any potentially sensitive receptors, where shadow flicker modelling indicates the amount could exceed 30 hours per year and 30 minutes per day, to ascertain the extent of existing natural visual screening in place. If not existing, the occurrence of shadow flickering during operation could be further investigated, and if confirmed, natural screening could be implemented to minimize the effect. | Shadow Flicker | EPC | ESIA 2023 | Health & Safety Management Plan | All Project Worksites
88 | Operation | ■ If grievances will be received or if natural visual screening at potentially sensitive receptors are found to be insufficient, investigations to implement architectural/structural screening, such as the installation of blinds, window shades, window tinting, awnings or fences, at affected receptors could be evaluated to further minimize the effect of shadow flicker. | Shadow Flicker | EPC | ESIA 2023 | Health & Safety Management Plan | All Project Worksites
89 | Operation | ■ Use of turbine control strategies which shut down turbines when shadow flicker is likely to occur. | Shadow Flicker | EPC | ESIA 2023 | Health & Safety Management Plan | All Project Worksites

## National Permitting
Ref. | Phase | Commitment | Topics | Responsibility | Source Document | Management Plan Reference | Project Worksite
0 | 1 | 2 | 3 | 4 | 5 | 6 | 8
1 | Construction/Operation | ■ Compliance with the conditions stipulated by regulatory acts of competent authorities; ■ Compliance with to GEO 57/2007; ■ Prohibition of harvesting/commercial trade of any species of fauna or flora with conservation value; ■ Approval and implementation of required measures for natural habitats restoration and populations of affected species in the event of an accident will be overseen by ANANP and carried out by the project owner; ■ Waste disposal is strictly prohibited within the protected sites; ■ In case of accidental harm to qualifying species of ROSCI0259 and ROSPA0145, ANANP must be promptly notified for the application of sanctions and cost recovery from the responsible party; ■ The construction phase will be scheduled to consider the post-natal period of Spermophilus citellus, i.e., late April to mid-May; ■ Vehicles traffic allowed only on established roads; ■ Implementation of pollution prevention measures for abiotic factors. | Biodiversity | Owner/EPC | Approval issued National Agency for Protected Areas (ANANP): | Biodiversity Management Plan, Pollution Prevention and Control Plan | All Project Worksites
2 | Construction/Operation | ■ Consistently monitor the impacted species and habitats outlined in the Specific Conservation Objectives for ROSCI0259 and ROSPA0145; | Biodiversity | Owner/EPC | Approval issued National Agency for Protected Areas: | Biodiversity Management Plan | All Project Worksites
3 | Construction/Operation | ■ Report the completion date of the approved works and coordinate with the reception commission. ■ Maintain the construction permit, technical documentation, and related project materials in pristine condition. ■ Dismantle temporary construction on the site within recommended days following the actual completion of the works. ■ Present the "Building Energy Performance Certificate" during the final inspection of the works. | Environmental Compliance | Owner/EPC | Construction Permit | Topsoil Management and Site Reinstatement Plan | All Project Worksites
4 | Construction/Operation | ■ Implement measures and notify authorities in case of archaeological chance finds during construction. | Cultural Heritage | Owner/EPC | Construction Permit | Cultural Heritage Management Plan | All Project Worksites
5 | Construction/Operation | ■ Adhere to specified conditions for public domain use, protection, and environmental preservation. | Designated and Protected Areas | Owner/EPC | Construction Permit | Traffic Management Plan | All Project Worksites
6 | Construction/Operation | ■ Apply for the "Fire Safety Authorization" post-reception or before starting Project facilities operation. | Community Health and Safety | Owner/EPC | Construction Permit | Health & Safety Management Plan | All Project Worksites
7 | Construction/Operation | ■ Ensure transportation of site of materials that cannot be reclaimed or repurposed, remaining after construction. | Waste and Wastewater | Owner/EPC | Construction Permit | Waste Management Plan | All Project Worksites
| Construction/Operation | ■ The works will be conducted while adhering to the conditions imposed by regulatory acts issued by authorities. ■ Approved machinery and transport means will be used to avoid spills of petroleum products and lubricants, noise, vibrations, etc. ■ Handling of fuels, materials, or other substances will be done in a way that prevents accidental spills on the ground or in water, avoiding dissolution and entrainment by precipitation water. | Environmental Compliance | Owner/EPC | Environmental Final Decision | Pollution Prevention and Control Plan | All Project Worksites
| Construction/Operation | ■ Waste resulting from the works will be collected in specially designated areas and then evacuated to specific waste disposal sites based on contracts. ■ Recyclable waste will be delivered to specialized units for recycling. ■ Construction material storage will be in specially designated areas. | Waste and Wastewater | Owner/EPC | Environmental Final Decision | Waste Management Plan | All Project Worksites
| Construction/Operation | ■ Construction material storage will be arranged to avoid blocking access routes (roads, driveways) and prevent wind or rainwater from carrying them away. ■ Optimization of the transport route for construction materials will be implemented to utilize existing roads only. ■ Necessary measures will be taken to prevent material losses during transportation. ■ Project implementation will be conducted without disrupting traffic in the area. ■ The construction site organization will be arranged to avoid affecting traffic. | Traffic | Owner/EPC | Environmental Final Decision | Traffic and transport Management Plan | All Project Worksites
| Construction/Operation | ■ Notify the competent environmental protection authority if new elements, unknown at the time of issuing regulatory acts, or modifications to the conditions that formed the basis for issuing regulatory acts, occur before the implementation of the changes. | Environmental Compliance | Owner | Environmental Final Decision | Pollution Prevention and Control Plan | All Project Worksites
| Construction/Operation | ■ At the completion of the works, the removal of the construction site setup will be carried out, and restoration work will be performed in the area. The land temporarily taken out of agricultural circulation will be returned to its initial state. The site will be cleaned, and the land will be restored to its original condition. ■ All specific activities will be strictly carried out within the approved perimeter, aiming to minimize the areas designated for construction or construction organization. | Environmental Compliance | Owner/EPC | Environmental Final Decision | Pollution Prevention and Control Plan | All Project Worksites
| Construction/Operation | ■ Electric cables will be buried to prevent the risk of increased bird mortality through contact with them. | Biodiversity | Owner/EPC | Environmental Final Decision | Biodiversity Management Plan | All Project Worksites
| Construction/Operation | ■ Follow the recommendation in the presentation memorandum, according to which, during the works, field teams must be accompanied by an expert in the field of biodiversity conservation. ■ Monitor the project's impact on habitats and species of community interest and promptly inform the authority responsible for the administration of protected natural areas (A.N.A.N.P. - Territorial Service Buzau) about any incidents that could have a negative impact. ■ Instruct the personnel and ensure compliance with the following prohibitions (according to the provisions of Emergency Ordinance no. 57/2007, Article 33): - Any form of harvesting, capture, killing, destruction, or harm to individuals in their natural environment at any stage of their biological cycle is prohibited. - Deliberate damage, destruction, or intentional collection of nests and/or eggs in nature, even if empty, is prohibited. - Intentional disturbance during the breeding, growth, hibernation, and migration periods is prohibited. - Deterioration and/or destruction of breeding or resting places are strictly prohibited. ■ If project personnel observe harm or fatalities among strictly protected bird or animal species report the incident promptly to the relevant regulatory authority. Actively assist in the retrieval of affected specimens and complete the necessary declaration. ■ In the case of an imminent threat with significant negative effects on achieving or maintaining a favorable conservation status of habitats or species, take immediate preventive measures and inform the relevant regulatory authority. ■ The monitoring will be conducted in accordance with the monitoring plan outlined in the adequacy assessment study and the environmental report prepared for the approval documentation of the Urban Planning Zoning (PUZ). This involves monitoring the populations of fauna species included in the standard form of the Natura 2000 site ROSCI0259 and ROSPA0145 during migration periods for a duration of 2 years. The focus will be on counting the number of dead birds in the turbine area. | Biodiversity | Owner | Environmental Final Decision | Biodiversity Management Plan | All Project Worksites
| Construction/Operation | ■ Activities necessary for carrying out the works will strictly take place on the surfaces described in the project, with the strict prohibition of occupying other lands and/or deforesting vegetation in the vicinity. ■ Crossing the watercourses with machinery in the project area is strictly forbidden. | Environmental Compliance | Owner/EPC | Environmental Final Decision | Pollution Prevention and Control Plan | All Project Worksites
| Construction/Operation | ■ Wind turbine stations must be signaled during the night with intermittent red lights with a large interval between two consecutive illuminations. | Community Health and Safety | Owner/EPC | Construction Permit | Health & Safety Management Plan | All Project Worksites